## Sheet1
Name | Type | Planned Critical Date | Workflow Name | Planned Start Date | Actual Shipment Date | Estimated Total Labor Hours | Delivery/On Site Date | SI #
0101 Front Bar @ Center Bar | Installation | 02/12/26 | 03wk install base line | 01/22/26 |  | 0
0102 Back Bar @ Center Bar | Installation | 02/12/26 | 03wk install base line | 01/22/26 |  | 0
0103 POS Station @ Center Bar | Installation | 03/05/26 | 03wk install base line | 02/12/26 |  | 0
0104 Screen Walls @ Center Bar | Installation | 03/05/26 | 03wk install base line | 02/12/26 |  | 0
0105 Column Paneling @ Center Bar | Installation | 03/05/26 | 03wk install base line | 02/12/26 |  | 0
0106 Ceiling Panels and Trim @ Center Bar | Installation | 01/29/26 | 03wk install base line | 01/08/26 |  | 0
0201 Front Bar @ Casino Bar #1 & #2 | Installation | 01/05/26 | 03wk install base line | 12/11/25 |  | 0
0202 Back Bar @ Casino Bar #1 & #2 | Installation | 01/05/26 | 03wk install base line | 12/11/25 |  | 0
0203 Metal Mesh/Metal Overhead Soffit @ Casino Bar #1 & #2 | Installation | 02/12/26 | 03wk install base line | 01/22/26 |  | 0
0300 Front Bar @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0301 Back Bar @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0302 Chilled Wine Display @ Steakhouse Restaurant | Installation | 02/18/26 | 03wk install base line | 01/28/26 |  | 0
0303 Wood Panel & Casing @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0304 Hostess stand @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0305 Hostess stand back counter @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0306 Vanities @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0307 Bar Service Stations & Panels @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0308 Main Dining Service Stations @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0309 Privat Dining Service Station @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0310 Patio Service Station @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0311 Fireplace @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0312 Patio Bar Slat Wall Panels @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0313 Patio Bar Footrail & Purse Hooks @ Steakhouse Restaurant | Installation | 04/09/26 | 03wk install base line | 03/19/26 |  | 0
0314 U-Shape Booth Wall Surround @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0315 Metal Jamb @ Steakhouse Restaurant | Installation | 03/26/26 | 03wk install base line | 03/05/26 |  | 0
0401 Tribal Display Cases @ Casino North Entry | Installation | 05/07/26 | 03wk install base line | 04/16/26 |  | 0
0402 Primed Soffit Trim & Acrylic Lenses @ Casino Ceiling | Installation | 05/07/26 | 03wk install base line | 04/16/26 |  | 0
0403 TV Surround Casing @ Casino | Installation | 05/07/26 | 03wk install base line | 04/16/26 |  | 0
0404 Door Casing & Cased Opening @ Casino | Installation | 05/07/26 | 03wk install base line | 04/16/26 |  | 0
0405 Paneling/Metal @ Specialty Gaming Façade | Installation | 05/07/26 | 03wk install base line | 04/16/26 |  | 0